## Project Planner
NSW Traffic Penalty Data Tool - Gantt Chart
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Stage 1 - Planning | 1 | 9 | 1 | 9 | 100% | bar: PERIODS 1 to PERIODS 9
1.1 Define team communication channels | 1 | 2 | 1 | 1 | 100% | bar: PERIODS 1 to PERIODS 2
1.2 Resource analysis and procurement | 1 | 2 | 1 | 1 | 100% | bar: PERIODS 1 to PERIODS 2
1.3 Evaluate current systems | 1 | 2 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
1.4 Develop a project overview | 1 | 2 | 1 | 2 | 100% | bar: PERIODS 1 to PERIODS 2
1.5 Establishing project scope | 2 | 3 | 2 | 3 | 100% | bar: PERIODS 2 to PERIODS 4
1.6 Develop a work breakdown structure | 2 | 4 | 4 | 5 | 100% | bar: PERIODS 2 to PERIODS 8
1.7 Analyse the dataset | 1 | 9 | 1 | 9 | 100% | bar: PERIODS 1 to PERIODS 9
1.8 Develop a Gantt chart | 1 | 9 | 2 | 8 | 100% | bar: PERIODS 1 to PERIODS 9
1.9 Define the project scope | 2 | 2 | 3 | 1 | 100% | bar: PERIODS 1 to PERIODS 3
Stage 2 - Design | 10 | 10 |  |  | 0% | bar: PERIODS 10 to PERIODS 20
2.1 Develop a system vision statement | 10 | 2 |  |  | 0% | bar: PERIODS 10 to PERIODS 11
2.2 Define project requirements | 10 | 2 |  |  | 0% | bar: PERIODS 10 to PERIODS 11
2.3 Develop software use cases | 12 | 3 |  |  | 0% | bar: PERIODS 12 to PERIODS 14
2.4 Develop software misuse cases | 12 | 3 |  |  | 0% | bar: PERIODS 12 to PERIODS 14
2.5 Define system components | 13 | 1 |  |  | 0% | bar: PERIODS 13
2.6 Define related software design | 13 | 3 |  |  | 0% | bar: PERIODS 13 to PERIODS 15
2.7 Define early user interface design | 14 | 3 |  |  | 0% | bar: PERIODS 14 to PERIODS 16
2.8 Develop a wireframe | 16 | 5 |  |  | 0% | bar: PERIODS 16 to PERIODS 20
Stage 3 - Software Development | 21 | 15 |  |  | 0% | bar: PERIODS 21 to PERIODS 35
3.1 Software unit allocations | 21 | 2 |  |  | 0% | bar: PERIODS 21 to PERIODS 22
3.2 Software prototyping | 23 | 4 |  |  | 0% | bar: PERIODS 23 to PERIODS 26
3.3 Software design progress reports | 22 | 2 |  |  | 0% | bar: PERIODS 22 to PERIODS 23
3.4 Software unit coding | 22 | 10 |  |  | 0% | bar: PERIODS 22 to PERIODS 31
3.5 Software unit debugging | 22 | 10 | bar: PERIODS 22 to PERIODS 31
3.6 Software unit incorporation | 31 | 2 | bar: PERIODS 31 to PERIODS 32
3.7 Integrated software testing | 32 | 3 | bar: PERIODS 32 to PERIODS 34
3.8 Major software finalization and publishing | 33 | 2 | bar: PERIODS 34 to PERIODS 35
Stage 4 - Implementation | 35 | 10 | bar: PERIODS 35 to PERIODS 44
4.1 Integration testing | 35 | 3 | bar: PERIODS 35 to PERIODS 37
4.2 Staff training | 35 | 5 | bar: PERIODS 35 to PERIODS 39
4.3 GUI finalizations | 37 | 3 | bar: PERIODS 37 to PERIODS 39
4.4 Installation performance monitoring | 38 | 2 | bar: PERIODS 38 to PERIODS 39
4.5 Bug fixes | 40 | 3 | bar: PERIODS 40 to PERIODS 42
4.6 User support documentation | 42 | 2 | bar: PERIODS 42 to PERIODS 43
4.7 Software support documentation | 43 | 2 | bar: PERIODS 43 to PERIODS 44
Stage 5 - Closure | 45 | 50 | bar: PERIODS 45 to PERIODS 49
5.1 Project finalization report | 45 | 2 | bar: PERIODS 45 to PERIODS 46
5.2 Team discussions | 46 | 3 | bar: PERIODS 46 to PERIODS 48
5.3 Team dispersion | 49 | 1 | bar: PERIODS 49