## Project Planner
Project Title
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Stage 1 - Planning | 1 | 9 |  |  | 0% | bar: PERIODS 1 to PERIODS 9
1.1 Evaluate current systems | 1 | 2 |  |  | 0% | bar: PERIODS 1 to PERIODS 2
1.2 Develop a project overview | 1 | 2 |  |  | 0% | bar: PERIODS 1 to PERIODS 2
1.3 Develop a work-breakdown structure | 1 | 4 |  |  | 0% | bar: PERIODS 1 to PERIODS 4
1.4 Analyse the dataset | 1 | 9 |  |  | 0% | bar: PERIODS 1 to PERIODS 9
1.5 Develop a gantt chart | 1 | 9 |  |  | 0% | bar: PERIODS 1 to PERIODS 9
1.6 Define the project scope | 2 | 3 |  |  | 0% | bar: PERIODS 2 to PERIODS 4
Stage 2 - Design | 1 | 9 |  |  | 0% | bar: PERIODS 1 to PERIODS 9
2.1 Develop a system vision statement | 1 | 2 |  |  | 0% | bar: PERIODS 1 to PERIODS 2
2.2 Define project requirements | 4 | 2 |  |  | 0% | bar: PERIODS 4 to PERIODS 5
2.3 Develop software use cases | 4 | 2 |  |  | 0% | bar: PERIODS 4 to PERIODS 5
2.4 Define system components | 5 | 2 |  |  | 0% | bar: PERIODS 5 to PERIODS 6
2.5 Define related software design | 5 | 2 |  |  | 0% | bar: PERIODS 5 to PERIODS 6
2.6 Define early user interface design | 6 | 2 |  |  | 0% | bar: PERIODS 6 to PERIODS 7
2.7 Develop a wireframe | 6 | 4 |  |  | 0% | bar: PERIODS 6 to PERIODS 9
Stage 3 - Implementation | 10 | 13 |  |  | 0% | bar: PERIODS 10 to PERIODS 22
Develop a testing plan | 10 | 4 |  |  | 0% | bar: PERIODS 10 to PERIODS 13
Develop a testing report | 14 | 2 |  |  | 0% | bar: PERIODS 14 to PERIODS 15
Create a user manual | 14 | 5 |  |  | 0% | bar: PERIODS 14 to PERIODS 18
Create a finalized data analysis report | 18 | 5 |  |  | 0% | bar: PERIODS 18 to PERIODS 22